## Instructions
Food Safety Implementation Project Plan
Document Code: FSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 22000:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] Project timing, PRP scope, hazard-control design, legal/customer requirements and verification depth must be tailored to the organization's products, processes, sites and food-chain role.
Use this workbook to plan implementation or major enhancement of an ISO 22000 FSMS. A separate Work Breakdown Library provides a ready-to-use implementation task catalogue; the Project Plan working table starts with five Illustrative Data rows and then remains blank for Actual Data.
1 | The first five Project Plan rows are Illustrative Data and are excluded from Actual KPI/Summary.
2 | Use Work Breakdown Library as a task catalogue; copy only relevant tasks into the working plan and mark them Actual Data.
3 | Replace role placeholders with named accountable owners and approved dates.
4 | Coordinate food safety, operations, hygiene, maintenance, supply chain, procurement, quality, HR, laboratories and top management.
5 | Do not finalize hazard controls before confirming process flow, PRPs, product/process information and hazard analysis inputs.
6 | Use verified legal, regulatory and customer food-safety requirements as project inputs.
7 | Track completion against evidence/deliverables, not elapsed time alone.
8 | Dashboard KPI uses Actual Data only; charts use Illustrative Data until Actual Data exists.
9 | Use Gap Analysis / Action Plan for detailed remediation so project tasks remain manageable.
10 | Official ISO sources are listed in Reference Data.

## Work Breakdown Library
FSMS Work Breakdown Library
Document Code: FSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 22000:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] Task library content is a template catalogue, not organizational project status. Copy only applicable tasks into the Project Plan working table.
Task ID | Phase | Workstream | Task / Activity | Deliverable / Evidence | Typical Owner Role | Priority | Use / Tailoring Note
FSP-001 | 1 - Initiate | Governance | Confirm executive sponsor and FSMS implementation governance. | Approved project governance / steering structure | Top Management | High | Tailor to site, product, process and project scope.
FSP-002 | 1 - Initiate | Objectives | Confirm project objectives, success criteria and intended FSMS outcomes. | Project charter / objectives | Project Manager | High | Tailor to site, product, process and project scope.
FSP-003 | 1 - Initiate | Scope | Define preliminary site, product, process, service and food-chain scope. | Approved implementation scope | Food Safety Team Leader | High | Tailor to site, product, process and project scope.
FSP-004 | 1 - Initiate | Food Safety Team | Appoint a competent food safety team and define responsibilities. | Food safety team appointment / responsibilities | Top Management | High | Tailor to site, product, process and project scope.
FSP-005 | 1 - Initiate | Plan | Baseline detailed implementation schedule, resources, communications and project risks. | Approved project plan | Project Manager | High | Tailor to site, product, process and project scope.
FSP-006 | 2 - Assess | Gap Analysis | Complete ISO 22000 FSMS gap analysis. | Gap analysis report | Lead Assessor | High | Tailor to site, product, process and project scope.
FSP-007 | 2 - Assess | Requirements | Identify applicable legal, regulatory, customer and internal food-safety requirements. | Requirements register | Food Safety / Regulatory Lead | High | Tailor to site, product, process and project scope.
FSP-008 | 2 - Assess | Context | Confirm context, interested parties, food-chain interfaces and relevant climate considerations. | Context / interested-party assessment | Food Safety Team Leader | Medium | Tailor to site, product, process and project scope.
FSP-009 | 2 - Assess | Process Mapping | Map process steps, inputs, outputs, rework, outsourced processes and interfaces. | Process flow diagrams | Operations / Process Owner | High | Tailor to site, product, process and project scope.
FSP-010 | 2 - Assess | PRP Review | Assess existing prerequisite programmes against site/process needs. | PRP assessment | Hygiene / Operations Manager | High | Tailor to site, product, process and project scope.
FSP-011 | 2 - Assess | Supplier Controls | Assess supplier approval, specifications, incoming controls and external provider risks. | Supplier-control assessment | Procurement / Quality Lead | High | Tailor to site, product, process and project scope.
FSP-012 | 2 - Assess | Traceability | Assess traceability and withdrawal/recall readiness. | Traceability assessment | Supply Chain Lead | High | Tailor to site, product, process and project scope.
FSP-013 | 2 - Assess | Emergency Readiness | Assess food-safety emergency preparedness and response. | Emergency-readiness assessment | Site Manager | Medium | Tailor to site, product, process and project scope.
FSP-014 | 2 - Assess | Monitoring Resources | Assess calibration, verification and measurement resources affecting food safety. | Monitoring-resource assessment | Quality / Maintenance Lead | Medium | Tailor to site, product, process and project scope.
FSP-015 | 2 - Assess | Action Planning | Prioritize validated gaps and approve the implementation action plan. | Approved FSMS action plan | FSMS Steering Group | High | Tailor to site, product, process and project scope.
FSP-016 | 3 - Design | FSMS Framework | Design FSMS process framework, governance and documented-information structure. | FSMS framework | Food Safety Team Leader | High | Tailor to site, product, process and project scope.
FSP-017 | 3 - Design | Policy / Objectives | Develop food-safety policy, objectives and indicators. | Policy/objectives package | Food Safety Team Leader | Medium | Tailor to site, product, process and project scope.
FSP-018 | 3 - Design | PRPs | Define/update site-appropriate prerequisite programmes and monitoring/verification responsibilities. | PRP programme set | Hygiene / Operations Manager | High | Tailor to site, product, process and project scope.
FSP-019 | 3 - Design | Product / Process Information | Define product characteristics, intended use, raw materials, process parameters and distribution information needed for hazard analysis. | Approved hazard-analysis inputs | Food Safety Team | High | Tailor to site, product, process and project scope.
FSP-020 | 3 - Design | Hazard Analysis | Identify reasonably expected food-safety hazards and assess significance using the approved method. | Hazard analysis | Food Safety Team | High | Tailor to site, product, process and project scope.
FSP-021 | 3 - Design | Control Measure Selection | Select and categorize control measures; define OPRP/CCP logic as applicable. | Control-measure selection record | Food Safety Team | High | Tailor to site, product, process and project scope.
FSP-022 | 3 - Design | Hazard Control Plan | Define action/critical criteria, monitoring, corrections, responsibilities and records for OPRPs/CCPs. | Hazard control plan | Food Safety Team Leader | High | Tailor to site, product, process and project scope.
FSP-023 | 3 - Design | Traceability / Recall | Design traceability, withdrawal and recall controls with test criteria. | Traceability / recall procedure | Supply Chain Lead | High | Tailor to site, product, process and project scope.
FSP-024 | 3 - Design | Nonconformity | Define control of potentially unsafe product, correction, evaluation and disposition. | Unsafe-product / nonconformity process | Quality Manager | High | Tailor to site, product, process and project scope.
FSP-025 | 3 - Design | Verification | Define verification plan covering PRPs, hazard controls, monitoring records and FSMS effectiveness. | Verification plan | Food Safety Team Leader | High | Tailor to site, product, process and project scope.
FSP-026 | 3 - Design | Emergency Response | Define food-safety emergency scenarios, communications and recovery responsibilities. | Emergency response plan | Site Manager | Medium | Tailor to site, product, process and project scope.
FSP-027 | 3 - Design | Communication | Define internal/external food-safety communication routes and escalation triggers. | Communication matrix | Food Safety Team Leader | Medium | Tailor to site, product, process and project scope.
FSP-028 | 4 - Implement | Document Deployment | Approve and issue controlled FSMS procedures, plans, forms and registers. | Controlled FSMS document set | Document Controller | High | Tailor to site, product, process and project scope.
FSP-029 | 4 - Implement | Training / Competence | Deliver role-based FSMS, hygiene, hazard-control and emergency training. | Training / competence evidence | HR / Training Lead | High | Tailor to site, product, process and project scope.
FSP-030 | 4 - Implement | PRP Operation | Implement PRPs and establish routine monitoring/verification evidence. | PRP operating records | Operations / Hygiene Manager | High | Tailor to site, product, process and project scope.
FSP-031 | 4 - Implement | Hazard Controls | Implement OPRP/CCP monitoring, corrections and escalation. | Hazard-control records | Operations Manager | High | Tailor to site, product, process and project scope.
FSP-032 | 4 - Implement | Supplier / Incoming | Implement approved supplier and incoming material controls. | Supplier / incoming records | Procurement / Quality Lead | Medium | Tailor to site, product, process and project scope.
FSP-033 | 4 - Implement | Traceability Test | Run traceability test and evaluate timing, reconciliation and gaps. | Traceability test report | Supply Chain Lead | High | Tailor to site, product, process and project scope.
FSP-034 | 4 - Implement | Emergency / Recall Exercise | Run suitable emergency or withdrawal/recall exercise. | Exercise report | Site Manager | High | Tailor to site, product, process and project scope.
FSP-035 | 5 - Validate | Verification | Execute planned verification of PRPs, hazard controls and records. | Verification results | Food Safety Team | High | Tailor to site, product, process and project scope.
FSP-036 | 5 - Validate | Internal Audit | Conduct internal FSMS audit. | Internal audit report | Lead Auditor | High | Tailor to site, product, process and project scope.
FSP-037 | 5 - Validate | Performance Review | Review monitoring trends, verification, complaints, incidents, supplier issues and objectives. | FSMS performance review | Food Safety Team Leader | High | Tailor to site, product, process and project scope.
FSP-038 | 5 - Validate | Corrective Action | Close high-priority validation/audit findings with evidence. | Corrective action evidence | Project Manager | High | Tailor to site, product, process and project scope.
FSP-039 | 5 - Validate | Management Review | Conduct implementation management review and approve readiness. | Management review minutes | Top Management | High | Tailor to site, product, process and project scope.
FSP-040 | 6 - Handover & Improve | Handover | Transfer document ownership, verification calendar, actions and governance to operations. | Operational handover pack | Project Manager | High | Tailor to site, product, process and project scope.
FSP-041 | 6 - Handover & Improve | Improvement Plan | Establish FSMS improvement backlog and review cadence. | FSMS improvement plan | Food Safety Team Leader | Medium | Tailor to site, product, process and project scope.
FSP-042 | 6 - Handover & Improve | Project Closure | Complete lessons learned, closure report and sponsor sign-off. | Project closure report | Project Manager | Medium | Tailor to site, product, process and project scope.

## Project Plan
Food Safety Implementation Project Plan - Main Tracker
Document Code: FSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 22000:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] The first 5 rows are Illustrative Data. Rows below are intentionally blank for Actual Data; use the Work Breakdown Library as a copy source.
Data Type | Task ID | Phase | Workstream | Task / Activity | Deliverable / Evidence | Owner Role | Priority | Predecessor(s) | Planned Start | Planned Finish | % Complete | Status | Schedule Flag | Actual Finish | Decision / Dependency | Reviewer | Notes
Example Data | EX-FSP-001 | 1 - Initiate | Governance | Confirm executive sponsor and food safety team governance. | Approved governance charter | Top Management | High |  | 2026-08-03 | 2026-08-07 | 100% | Completed |  |  |  | Project Manager | Illustrative Data
Example Data | EX-FSP-010 | 2 - Assess | PRP Review | Assess prerequisite programmes against site and process conditions. | PRP assessment | Hygiene Manager | High | EX-FSP-001 | 2026-08-17 | 2026-09-04 | 85% | In Progress |  |  | One sanitation-zone review remains open | Food Safety Team Leader | Illustrative Data
Example Data | EX-FSP-020 | 3 - Design | Hazard Analysis | Complete hazard analysis using approved product/process information. | Hazard analysis | Food Safety Team | High | EX-FSP-010 | 2026-09-07 | 2026-09-30 | 60% | In Progress |  |  | Supplier allergen data pending for one ingredient group | Project Manager | Illustrative Data
Example Data | EX-FSP-033 | 4 - Implement | Traceability Test | Run forward/backward traceability test and evaluate reconciliation. | Traceability test report | Supply Chain Lead | Medium | EX-FSP-020 | 2026-10-15 | 2026-10-16 | 0% | Blocked |  |  | Test postponed until ERP lot-code mapping update is complete | Food Safety Team Leader | Illustrative Data
Example Data | EX-FSP-036 | 5 - Validate | Internal Audit | Conduct internal FSMS audit using operating evidence. | Internal audit report | Lead Auditor | Low | EX-FSP-033 | 2026-11-16 | 2026-11-27 | 0% | Not Started |  |  | Dependent on sufficient operating records | Project Manager | Illustrative Data
Formulas:
Schedule Flag = IF([Data Type]<>"Actual Data","",IF(OR([Status]="Completed",[Status]="N/A"),[Status],IF([Planned Finish]="","",IF([Planned Finish]<TODAY(),"Overdue",IF([Planned Finish]-TODAY()<=7,"Due Soon","On Track")))))

## Dashboard
Food Safety Implementation Dashboard
Document Code: FSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 22000:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] Example Data is used only to demonstrate charts while no Actual Data exists. KPI/Summary always excludes Example Data.
Chart Data Mode | Illustrative Data
Actual KPI | Result
Actual Tasks | 0
Completed | 0
In Progress | 0
Blocked | 0
Not Started | 0
Overdue | 0
High Priority Open | 0
Average % Complete | 0%
Actual Completion % | 0%
Example Rows (excluded) | 5

## Chart Data
Chart Data - FSMS Project Plan
Document Code: FSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 22000:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Chart Data Mode | Value
Mode | Illustrative Data
Status | Count | Phase | Count
Not Started | 1 | 1 - Initiate | 1
In Progress | 2 | 2 - Assess | 1
Blocked | 1 | 3 - Design | 1
Completed | 1 | 4 - Implement | 1
N/A | 0 | 5 - Validate | 1
|  | 6 - Handover & Improve | 0

## Reference Data
Reference Data
Document Code: FSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 22000:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
List | Value | Description | Source / Note
Data Type | Example Data | Illustrative row; excluded from Actual KPI/Summary.
Data Type | Actual Data | Operational row; included in Actual KPI/Summary.
Priority | High
Priority | Medium
Priority | Low
Standard | ISO 22000:2018 | Current published FSMS standard; confirmed current by ISO. | https://www.iso.org/standard/65464.html
Amendment | ISO 22000:2018/Amd 1:2024 | Published climate-action amendment applying to ISO 22000:2018. | https://www.iso.org/standard/88410.html
Status Note | ISO/DIS 22000 | Revision is under development; not used as the controlled baseline in this toolkit. | https://www.iso.org/standard/88794.html
Phase | 1 - Initiate
Phase | 2 - Assess
Phase | 3 - Design
Phase | 4 - Implement
Phase | 5 - Validate
Phase | 6 - Handover & Improve
Status | Not Started
Status | In Progress
Status | Blocked
Status | Completed
Status | N/A
[Note] Food-safety legal, regulatory, customer, product, allergen, labeling, import/export and sector requirements must be verified for the relevant jurisdiction, products and food-chain activities before controlled use.

## Revision History
Revision History
Document Code: FSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 22000:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Version | Date | Description
1.0 | 2026-09-18 | Initial issue