## Instructions
Health & Safety Implementation Project Plan
Document Code: OHSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 45001:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Purpose
Use this workbook to plan and control OH&SMS implementation from project initiation through hazard/risk control, internal audit, management review and certification readiness. Dates are intentionally blank so the organization can set a realistic implementation schedule.
1 | Confirm sponsor, OH&S project lead, implementation objectives and worker-participation arrangements.
2 | Set dates based on workforce, operations, hazards, legal requirements and resource availability.
3 | Assign one accountable owner for each task and use Notes for supporting contributors.
4 | Sequence work so hazard/risk controls and worker consultation occur before relying on documents as evidence.
5 | Update Status and % Complete during project reviews.
6 | Use Dashboard to identify overdue, blocked and high-priority work.
7 | Certification readiness should be based on implemented, operating and evidenced arrangements, not document completion alone.

## Project Plan
OH&SMS Implementation Project Plan - Main Tracker
Document Code: OHSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 45001:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Task ID | Phase | Task | Practical Deliverable | Owner | Priority | Start Date | Due Date | Status | % Complete | Dependency | Schedule Flag | Evidence / Link | Notes
P1-01 | 1. Initiation | Appoint project sponsor and OH&S implementation lead | Named sponsor and implementation lead |  | Medium |  |  | Not Started | 0%
P1-02 | 1. Initiation | Define implementation objectives and governance | Approved implementation brief / charter |  | Medium |  |  | Not Started | 0%
P1-03 | 1. Initiation | Identify implementation team and worker representatives | Implementation team and participation structure |  | Medium |  |  | Not Started | 0%
P1-04 | 1. Initiation | Confirm applicable standard baseline and certification intent | Baseline and project assumptions |  | Medium |  |  | Not Started | 0%
P2-01 | 2. Context & Scope | Analyze internal/external OH&S context | Context analysis including relevant climate-related considerations |  | Medium |  |  | Not Started | 0%
P2-02 | 2. Context & Scope | Identify workers and other interested parties | Interested parties and relevant needs/expectations |  | Medium |  |  | Not Started | 0%
P2-03 | 2. Context & Scope | Identify applicable legal and other requirements sources | Initial obligations source list |  | Medium |  |  | Not Started | 0%
P2-04 | 2. Context & Scope | Define OH&SMS scope and boundaries | Approved OH&SMS scope |  | Medium |  |  | Not Started | 0%
P2-05 | 2. Context & Scope | Map OH&SMS processes and interfaces | OH&SMS process map |  | Medium |  |  | Not Started | 0%
P3-01 | 3. Gap Analysis | Perform OH&SMS gap analysis | Completed gap assessment with evidence |  | Medium |  |  | Not Started | 0%
P3-02 | 3. Gap Analysis | Prioritize gaps and assign actions | Approved gap action plan |  | Medium |  |  | Not Started | 0%
P4-01 | 4. Hazard & Risk | Define hazard identification and OH&S risk method | Approved method and risk criteria |  | Medium |  |  | Not Started | 0%
P4-02 | 4. Hazard & Risk | Identify routine and non-routine activities and work groups | Activity / exposure inventory |  | Medium |  |  | Not Started | 0%
P4-03 | 4. Hazard & Risk | Identify hazards including human, organizational and external factors | Hazard inventory |  | Medium |  |  | Not Started | 0%
P4-04 | 4. Hazard & Risk | Assess OH&S risks and identify existing controls | Hazard & risk register |  | Medium |  |  | Not Started | 0%
P4-05 | 4. Hazard & Risk | Identify OH&S opportunities | OH&S opportunities register |  | Medium |  |  | Not Started | 0%
P4-06 | 4. Hazard & Risk | Prioritize risk-reduction actions using hierarchy of controls | Risk-control improvement plan |  | Medium |  |  | Not Started | 0%
P5-01 | 5. Leadership & Participation | Approve OH&S policy | Approved and communicated OH&S policy |  | Medium |  |  | Not Started | 0%
P5-02 | 5. Leadership & Participation | Assign OH&S roles, responsibilities and authorities | Roles/responsibilities matrix |  | Medium |  |  | Not Started | 0%
P5-03 | 5. Leadership & Participation | Establish worker consultation and participation arrangements | Consultation/participation procedure and schedule |  | Medium |  |  | Not Started | 0%
P5-04 | 5. Leadership & Participation | Establish OH&S objectives and indicators | Objectives / KPI register |  | Medium |  |  | Not Started | 0%
P6-01 | 6. Support & Compliance | Establish legal/other requirements register | Current obligations register |  | Medium |  |  | Not Started | 0%
P6-02 | 6. Support & Compliance | Establish competence, training and awareness controls | Training matrix and awareness plan |  | Medium |  |  | Not Started | 0%
P6-03 | 6. Support & Compliance | Establish OH&S communication arrangements | Communication method / responsibilities |  | Medium |  |  | Not Started | 0%
P6-04 | 6. Support & Compliance | Establish documented information controls | Document/record control implemented |  | Medium |  |  | Not Started | 0%
P7-01 | 7. Operational Control | Implement operational controls for significant OH&S risks | Operating controls and evidence |  | Medium |  |  | Not Started | 0%
P7-02 | 7. Operational Control | Apply hierarchy of controls to priority risks | Risk-reduction actions and evidence |  | Medium |  |  | Not Started | 0%
P7-03 | 7. Operational Control | Implement management of change | Change-risk review process |  | Medium |  |  | Not Started | 0%
P7-04 | 7. Operational Control | Implement procurement, contractor and outsourcing OH&S controls | Supplier/contractor controls and evidence |  | Medium |  |  | Not Started | 0%
P7-05 | 7. Operational Control | Establish emergency preparedness and response | Emergency plans and response arrangements |  | Medium |  |  | Not Started | 0%
P7-06 | 7. Operational Control | Conduct emergency drills / tests | Drill results and actions |  | Medium |  |  | Not Started | 0%
P8-01 | 8. Performance & Improvement | Establish monitoring, inspection and measurement programme | Monitoring / inspection plan |  | Medium |  |  | Not Started | 0%
P8-02 | 8. Performance & Improvement | Establish compliance evaluation process | Compliance evaluation schedule and records |  | Medium |  |  | Not Started | 0%
P8-03 | 8. Performance & Improvement | Implement incident/near-miss reporting and investigation | Incident process and records |  | Medium |  |  | Not Started | 0%
P8-04 | 8. Performance & Improvement | Implement corrective action and effectiveness review | CAR records and verification |  | Medium |  |  | Not Started | 0%
P8-05 | 8. Performance & Improvement | Operate objectives/KPI monitoring | Performance evidence and trends |  | Medium |  |  | Not Started | 0%
P9-01 | 9. Assurance | Conduct internal OH&S audit | Audit report and findings |  | Medium |  |  | Not Started | 0%
P9-02 | 9. Assurance | Close audit findings / corrective actions | Verified closure evidence |  | Medium |  |  | Not Started | 0%
P9-03 | 9. Assurance | Conduct management review | Management review minutes and actions |  | Medium |  |  | Not Started | 0%
P10-01 | 10. Readiness | Complete certification readiness review | Readiness assessment and residual actions |  | Medium |  |  | Not Started | 0%
P10-02 | 10. Readiness | Close critical readiness gaps | Critical actions closed with evidence |  | Medium |  |  | Not Started | 0%
P10-03 | 10. Readiness | Prepare audit logistics and evidence index | Audit logistics / evidence index |  | Medium |  |  | Not Started | 0%
Formulas:
Schedule Flag = IF([Status]="Completed","Completed",IF([Due Date]="","",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]-TODAY()<=7,"Due Soon","On Track"))))

## Dashboard
OH&SMS Implementation Project Dashboard
Document Code: OHSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 45001:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
KPI | Result | Status | Count
Total Tasks | 42 | Not Started | 42
Completed | 0 | In Progress | 0
In Progress | 0 | Blocked | 0
Blocked | 0 | Completed | 0
Not Started | 42
Overdue | 0
High Priority | 0
Average % Complete | 0%

## Reference Data
List | Value
Priority | High
Priority | Medium
Priority | Low
Status | Not Started
Status | In Progress
Status | Blocked
Status | Completed

## Revision History
Revision History
Document Code: OHSMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 45001:2018 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Version | Date | Description
1.0 | 2026-09-18 | Initial issue