## Instructions
Information Security Implementation Project Plan
Document Code: ISMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27001:2022 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Purpose
Use this workbook to plan and control ISMS implementation from project initiation through internal audit, management review and certification readiness. Dates are intentionally blank so the organization can set a realistic implementation schedule.
1 | Confirm project sponsor, ISMS manager, scope and implementation objectives.
2 | Set planned start/due dates based on organization size, current maturity and resource availability.
3 | Assign one accountable owner for each task and record supporting contributors in Notes if needed.
4 | Use dependencies to sequence work; avoid completing documentation without implementation evidence.
5 | Update % Complete and Status during project reviews.
6 | Use the Dashboard to identify overdue, blocked and high-priority work.
7 | Certification readiness should be based on implemented, operating and evidenced controls—not document completion alone.

## Project Plan
ISMS Implementation Project Plan - Main Tracker
Document Code: ISMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27001:2022 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Task ID | Phase | Task | Practical Deliverable | Owner | Priority | Start Date | Due Date | Status | % Complete | Dependency | Schedule Flag | Evidence / Link | Notes
P1-01 | 1. Initiation | Appoint project sponsor and ISMS manager | Named sponsor, ISMS manager and governance route |  | Medium |  |  | Not Started | 0%
P1-02 | 1. Initiation | Define implementation objectives and project governance | Approved project charter / implementation brief |  | Medium |  |  | Not Started | 0%
P1-03 | 1. Initiation | Identify key stakeholders and implementation team | Stakeholder list and implementation team |  | Medium |  |  | Not Started | 0%
P1-04 | 1. Initiation | Confirm baseline standard and legal/regulatory context | Baseline confirmed; applicable obligations review started |  | Medium |  |  | Not Started | 0%
P2-01 | 2. Scope & Context | Analyze internal/external context | Context analysis relevant to information security |  | Medium |  |  | Not Started | 0%
P2-02 | 2. Scope & Context | Identify interested parties and security expectations | Interested parties and needs register |  | Medium |  |  | Not Started | 0%
P2-03 | 2. Scope & Context | Define ISMS scope and boundaries | Approved ISMS scope |  | Medium |  |  | Not Started | 0%
P2-04 | 2. Scope & Context | Map ISMS processes and interfaces | ISMS process map / governance interfaces |  | Medium |  |  | Not Started | 0%
P3-01 | 3. Gap Analysis | Perform ISMS gap analysis | Completed gap assessment with evidence |  | Medium |  |  | Not Started | 0%
P3-02 | 3. Gap Analysis | Prioritize gaps and implementation actions | Approved gap action plan |  | Medium |  |  | Not Started | 0%
P4-01 | 4. Risk Management | Define risk assessment and treatment method | Approved risk method and criteria |  | Medium |  |  | Not Started | 0%
P4-02 | 4. Risk Management | Build information asset / information inventory | Current asset/information inventory |  | Medium |  |  | Not Started | 0%
P4-03 | 4. Risk Management | Perform information security risk assessment | Risk register with owners and ratings |  | Medium |  |  | Not Started | 0%
P4-04 | 4. Risk Management | Select risk treatments | Treatment decisions linked to risks |  | Medium |  |  | Not Started | 0%
P4-05 | 4. Risk Management | Develop Statement of Applicability | SoA with control applicability and justification |  | Medium |  |  | Not Started | 0%
P4-06 | 4. Risk Management | Develop risk treatment plan | Treatment actions, owners, resources and due dates |  | Medium |  |  | Not Started | 0%
P5-01 | 5. Governance & Policy | Approve information security policy | Approved and communicated policy |  | Medium |  |  | Not Started | 0%
P5-02 | 5. Governance & Policy | Assign ISMS roles and responsibilities | Defined owners and authorities |  | Medium |  |  | Not Started | 0%
P5-03 | 5. Governance & Policy | Set information security objectives and indicators | Objectives / KPI register |  | Medium |  |  | Not Started | 0%
P5-04 | 5. Governance & Policy | Establish documented information controls | Document/record control implemented |  | Medium |  |  | Not Started | 0%
P6-01 | 6. Control Implementation | Implement organizational security controls | Implemented controls with operating evidence |  | Medium |  |  | Not Started | 0%
P6-02 | 6. Control Implementation | Implement people security controls | People lifecycle, awareness and training controls |  | Medium |  |  | Not Started | 0%
P6-03 | 6. Control Implementation | Implement physical security controls | Physical access/environment/security controls |  | Medium |  |  | Not Started | 0%
P6-04 | 6. Control Implementation | Implement technological security controls | Access, configuration, logging, vulnerability, backup and related technical controls |  | Medium |  |  | Not Started | 0%
P6-05 | 6. Control Implementation | Implement supplier security controls | Security due diligence, contracts and monitoring |  | Medium |  |  | Not Started | 0%
P6-06 | 6. Control Implementation | Implement incident management | Incident reporting, response, lessons learned and records |  | Medium |  |  | Not Started | 0%
P6-07 | 6. Control Implementation | Implement security continuity / ICT readiness | Continuity and recovery arrangements with test evidence |  | Medium |  |  | Not Started | 0%
P7-01 | 7. Awareness & Operation | Deliver organization-wide security awareness | Awareness completion evidence |  | Medium |  |  | Not Started | 0%
P7-02 | 7. Awareness & Operation | Deliver role-based security training | Role-based competence evidence |  | Medium |  |  | Not Started | 0%
P7-03 | 7. Awareness & Operation | Operate ISMS controls and collect evidence | Operating records across defined evidence period |  | Medium |  |  | Not Started | 0%
P8-01 | 8. Performance Evaluation | Monitor objectives, controls and ISMS performance | KPI/control monitoring results |  | Medium |  |  | Not Started | 0%
P8-02 | 8. Performance Evaluation | Conduct internal audit | Audit report and findings |  | Medium |  |  | Not Started | 0%
P8-03 | 8. Performance Evaluation | Close audit findings / corrective actions | Verified corrective action records |  | Medium |  |  | Not Started | 0%
P8-04 | 8. Performance Evaluation | Conduct management review | Management review minutes and actions |  | Medium |  |  | Not Started | 0%
P9-01 | 9. Readiness | Complete certification readiness review | Readiness findings and residual actions |  | Medium |  |  | Not Started | 0%
P9-02 | 9. Readiness | Close critical readiness gaps | Critical actions closed with evidence |  | Medium |  |  | Not Started | 0%
P9-03 | 9. Readiness | Prepare certification logistics and evidence index | Audit logistics and evidence index |  | Medium |  |  | Not Started | 0%
Formulas:
Schedule Flag = IF([Status]="Completed","Completed",IF([Due Date]="","",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]-TODAY()<=7,"Due Soon","On Track"))))

## Dashboard
ISMS Implementation Project Dashboard
Document Code: ISMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27001:2022 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
KPI | Result | Status | Count
Total Tasks | 37 | Not Started | 37
Completed | 0 | In Progress | 0
In Progress | 0 | Blocked | 0
Blocked | 0 | Completed | 0
Not Started | 37
Overdue | 0
High Priority | 0
Average % Complete | 0%

## Reference Data
List | Value
Priority | High
Priority | Medium
Priority | Low
Status | Not Started
Status | In Progress
Status | Blocked
Status | Completed

## Revision History
Revision History
Document Code: ISMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27001:2022 + Amd 1:2024 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Version | Date | Description
1.0 | 2026-09-18 | Initial issue