## Dashboard
ISO 9001 Project Plan
Document Code | QMS-PLN-001 | Version | 1.0 | Effective Date | 2026-09-18
Owner | Quality Manager | Standard | ISO 9001:2026 | Compatibility | Excel 2007+
Website | www.iso-toolkits.org | Email | info@iso-toolkits.org | Source | https://www.iso.org/standard/9001
Use this plan to sequence implementation, assign ownership and track completion. Enter planned dates and actual project evidence; the template contains no assumed organization dates.
Total Tasks |  |  | Complete |  |  | In Progress | Overdue
30 |  |  | 0 |  |  | 0 | 0
Phase | Total Tasks | Complete
1. Initiation | 5 | 0
2. Gap Analysis | 6 | 0
3. QMS Design | 6 | 0
4. Implementation | 5 | 0
5. Evaluation | 4 | 0
6. Certification Readiness | 4 | 0
Overall Completion
0%

## Project Plan
ISO 9001:2026 Implementation Project Plan
Document Code | QMS-PLN-001 | Version | 1.0 | Effective Date | 2026-09-18
Owner | Quality Manager | Applied Standard | ISO 9001:2026 | Compatibility | Excel 2007+
Website | www.iso-toolkits.org | Email | info@iso-toolkits.org | Source | https://www.iso.org/standard/9001
Template tasks are a practical starting point. Tailor sequencing, owners, dates and deliverables to the organization and certification strategy.
Task ID | Phase | Activity | Deliverable / Exit Criteria | Owner | Planned Start | Planned Finish | Duration Days | Priority | Status | % Complete | Schedule Flag | Dependency | Evidence / Link
P01 | 1. Initiation | Confirm project sponsor and project lead | Named sponsor and project lead with authority to coordinate implementation |  |  |  |  | High | Not Started | 0%
P02 | 1. Initiation | Confirm implementation objective and certification intent | Agreed implementation objective and target certification approach |  |  |  |  | High | Not Started | 0% |  | P01
P03 | 1. Initiation | Establish implementation team and governance | Core team, responsibilities and meeting cadence agreed |  |  |  |  | High | Not Started | 0% |  | P01
P04 | 1. Initiation | Conduct leadership / project awareness briefing | Leadership understands project purpose, role and expected decisions |  |  |  |  | Medium | Not Started | 0% |  | P01
P05 | 1. Initiation | Set project communication and evidence storage method | Common location for plans, evidence, actions and controlled outputs |  |  |  |  | Medium | Not Started | 0% |  | P03
P06 | 2. Gap Analysis | Define initial QMS scope boundaries | Draft scope covering products/services, locations and relevant processes |  |  |  |  | High | Not Started | 0% |  | P02
P07 | 2. Gap Analysis | Identify internal and external context | Relevant context factors documented for implementation planning |  |  |  |  | High | Not Started | 0% |  | P06
P08 | 2. Gap Analysis | Identify relevant interested parties and requirements | Relevant parties and requirements recorded |  |  |  |  | High | Not Started | 0% |  | P06
P09 | 2. Gap Analysis | Map QMS processes and interfaces | Process map or interaction matrix with owners and interfaces |  |  |  |  | High | Not Started | 0% |  | P07
P10 | 2. Gap Analysis | Perform ISO 9001:2026 gap analysis | Current state, evidence and gaps assessed across applicable requirements |  |  |  |  | High | Not Started | 0% |  | P07
P11 | 2. Gap Analysis | Prioritize gaps and approve implementation action plan | Prioritized action list with owners and due dates |  |  |  |  | High | Not Started | 0% |  | P10
P12 | 3. QMS Design | Develop / update Quality Policy | Policy aligned to organization direction and QMS intent |  |  |  |  | High | Not Started | 0% |  | P07
P13 | 3. QMS Design | Set quality objectives and indicators | Objectives, measures, targets, owners and review frequency defined |  |  |  |  | High | Not Started | 0% |  | P12
P14 | 3. QMS Design | Define roles, responsibilities and process ownership | Key QMS responsibilities communicated |  |  |  |  | High | Not Started | 0% |  | P09
P15 | 3. QMS Design | Establish risk and opportunity approach | Relevant QMS risks/opportunities and actions integrated into planning |  |  |  |  | High | Not Started | 0% |  | P10
P16 | 3. QMS Design | Establish documented information controls | Controls for creation, approval, access, change, retention and disposition defined |  |  |  |  | Medium | Not Started | 0% |  | P11
P17 | 3. QMS Design | Build QMS document map | Required and useful procedures, forms, records and guidance identified |  |  |  |  | Medium | Not Started | 0% |  | P16
P18 | 4. Implementation | Implement process controls and required records | Processes operate using defined controls and retain appropriate evidence |  |  |  |  | High | Not Started | 0% |  | P11
P19 | 4. Implementation | Confirm competence needs and close priority gaps | Competence requirements and evidence available for relevant roles |  |  |  |  | High | Not Started | 0% |  | P18
P20 | 4. Implementation | Implement monitoring and measurement arrangements | Process and QMS performance data are collected and reviewed |  |  |  |  | High | Not Started | 0% |  | P13
P21 | 4. Implementation | Implement supplier / external provider controls as applicable | Selection, monitoring and control evidence available where relevant |  |  |  |  | Medium | Not Started | 0% |  | P18
P22 | 4. Implementation | Operate nonconformity and corrective action process | Issues are corrected, causes addressed where needed and actions tracked |  |  |  |  | High | Not Started | 0% |  | P18
P23 | 5. Evaluation | Plan internal audit program | Audit scope, timing, criteria and auditor independence arranged |  |  |  |  | High | Not Started | 0% |  | P18
P24 | 5. Evaluation | Conduct full-system internal audit | Audit evidence, findings and report completed |  |  |  |  | High | Not Started | 0% |  | P23
P25 | 5. Evaluation | Close internal audit nonconformities | Corrections and corrective actions implemented and verified as appropriate |  |  |  |  | High | Not Started | 0% |  | P24
P26 | 5. Evaluation | Conduct management review | Required QMS performance information reviewed and decisions/actions recorded |  |  |  |  | High | Not Started | 0% |  | P24
P27 | 6. Certification Readiness | Perform certification readiness review | Open critical gaps identified and assigned before certification audit |  |  |  |  | High | Not Started | 0% |  | P25
P28 | 6. Certification Readiness | Close readiness actions | Critical readiness actions completed with evidence |  |  |  |  | High | Not Started | 0% |  | P27
P29 | 6. Certification Readiness | Prepare Stage 1 / documentation readiness evidence | Scope, key QMS information and implementation evidence organized |  |  |  |  | Medium | Not Started | 0% |  | P28
P30 | 6. Certification Readiness | Prepare Stage 2 / implementation evidence and audit logistics | Process evidence, personnel and logistics ready for certification audit |  |  |  |  | Medium | Not Started | 0% |  | P29
Formulas:
Schedule Flag = IF(OR([Status]="Complete",[Planned Finish]=""),"",IF([Planned Finish]<TODAY(),"Overdue",IF([Planned Finish]<=TODAY()+7,"Due Soon","On Track")))

## Reference Data
Reference Data
Document Code | QMS-PLN-001 | Version | 1.0 | Effective Date | 2026-09-18
Owner | Quality Manager | Applied Standard | ISO 9001:2026 | Compatibility | Excel 2007+
Website | www.iso-toolkits.org | Email | info@iso-toolkits.org | Source | https://www.iso.org/standard/9001
Status | Priority | Phase | Reference
Not Started | High | 1. Initiation | Current standard: ISO 9001:2026
In Progress | Medium | 2. Gap Analysis | https://www.iso.org/standard/9001
Blocked | Low | 3. QMS Design | Tasks are implementation guidance, not quoted ISO requirements.
Complete |  | 4. Implementation
Not Applicable |  | 5. Evaluation
6. Certification Readiness